## Slide 1
CORPORATE & FOUNDATION RELATIONS • STANDARD OPERATING PROCEDURE
Complex Industry-Supported Research Gift Workflow
An 11-stage decision framework for evaluating, structuring, and stewarding industry-funded research gifts — validated by the PBM Capital / Manning Institute gift
v1.0 — Draft for Review
UVA Development — CFR
PROCESS FLOW — ELEVEN STAGES, TWO DECISION GATES
01 Discovery
Understand donor intent
02 Funding Pathway
Gift · Grant · Contract
03 Stakeholder Map
Assemble the team
04 Complexity Check
Escalate if triggered
05 Compliance Review
Protect independence
06 Documentation
Gift Agmt · SOW · COI
07 Financial Review
Fees · F&A · budget
08 Multi-Institution
Coordinate partners
09 Accounting & Credit
Hard · soft · CRM
10 Stewardship
Not reporting
11 Relationship Growth
Next opportunity
START
DECISION GATE — CHOOSE THE FUNDING VEHICLE
Criterion | Gift | Sponsored Research | Contract
Unrestricted support | ✓ |  | 
Specific deliverables |  | ✓ | ✓
Publication restrictions |  | ✓ | ✓
IP expectations |  | ✓ | ✓
Donor directs research |  | ✓ | ✓
General stewardship only | ✓ |  | 
SOW should include
Research objectives, themes, scope, faculty collaboration, general use of funds.
SOW should avoid
Deliverables, milestones, deadlines, sponsor direction, publication requirements.
STAKEHOLDER CHAIN — ONE CFR LEAD QUARTERBACKS
1. Corporate Relations
2. Development Officer
3. Dept. Leadership
4. Health Development*
5. Office of Sponsored Programs
6. Gift Administration
7. Finance
8. Legal
9. Research Administration
10. Collaborating Institution
*if applicable — each link has an assigned owner: relationship, agreement, budget, compliance, accounting, or stewardship lead.
ESCALATE IMMEDIATELY IF THE GIFT INVOLVES:
Multiple institutions · Industry partner · International entity · Human subjects · Export controls · Intellectual property · Existing equity · Conflict of interest · Licensing · Technology transfer · Multiple funding entities · Pass-through funding
LESSONS LEARNED — PBM CAPITAL GIFT
Donor intent changed over time.
→ Revisit donor motivation throughout the process.
OSP became a critical partner.
→ Engage OSP early for any research-related industry gift.
Multi-party gifts need special accounting.
→ Involve Gift Administration before agreements are finalized.
The 5% Health Dev. fee reduced research funds.
→ Discuss fee treatment early; consider a separate unrestricted gift.
Many offices touched the project.
→ Assign one CFR lead to quarterback the donor experience.
Guiding Principle: Every complex industry gift should leave the University with a stronger process than it had before. Our role is to align institutional partners, translate complexity for donors, protect the University's interests, and create an experience that makes industry partners want to work with UVA again.